# 30-Day Food Delivery MVP Roadmap for Iraq

## Solo Developer Production Checklist

## EXECUTIVE SUMMARY

Timeline: 30 days (4 weeks)
Developer: Solo (you)
Goal: Production-ready Talabat-like food delivery app for Iraq
Launch readiness: End of Week 4

Critical Path: Backend data model → Core APIs → Mobile customer flow → Driver app → Real-time tracking → Store submission

## PRIORITY MATRIX (CUT-LINE MVP)

| Priority | Feature | Impact if Cut | Cut After |
| --- | --- | --- | --- |
| P0 (MUST) | Customer browse/order | App doesn't work | Never |
| P0 | Restaurant receives orders | Can't fulfill orders | Never |
| P0 | Driver sees & completes orders | No delivery | Never |
| P0 | Basic order status updates | Customer blind | Never |
| P0 | Push notifications (order placed/driver assigned) | Poor UX | Never |
| P1 (SHOULD) | Live driver tracking on map | UX downgrade but workable | Week 3 |
| P1 | In-app chat | Use phone/external chat | Week 3 |
| P1 | Restaurant admin self-service | Manual workarounds | Week 3 |
| P1 | Order history | Can't reorder easily | Week 3 |
| P2 (NICE) | Social login (Google/Apple) | Email works | Week 2 |
| P2 | Advanced search/filters | Browse works | Week 2 |
| P2 | Ratings & reviews | Launch without | Week 2 |
| P2 | Promo codes | Add post-launch | Week 1 |

If you lose 1 week: Cut P2 entirely, keep chat basic (text only, no images), skip restaurant self-service (admin adds menus manually), simplify driver tracking (periodic updates vs continuous).

## RISK REGISTER

| Risk | Probability | Impact | Mitigation | Contingency |
| --- | --- | --- | --- | --- |
| Real-time architecture complexity | High | High | Use Firestore listeners (managed) | Fall back to polling every 10s |
| RTL bugs in Flutter | Medium | Medium | Test early (Day 3), use Intl package | Budget 2 days for fixes |
| App Store review delays | Medium | High | Submit by Day 25 with buffer | Have TestFlight/internal track ready |
| Firebase costs spike | Low | Medium | Set budget alerts, monitor usage | Cache aggressively, use indexes |
| Mapbox integration issues | Medium | Medium | Integrate by Day 5, test thoroughly | Fall back to Google Maps (costs more) |
| Auth flow bugs (social login) | Medium | Low | Test extensively, or cut social login | Email/password only |
| Driver GPS tracking battery drain | Medium | Medium | Use background location efficiently | Reduce update frequency |
| Iraq payment gateway unavailable | Low | High | COD only in MVP (already planned) | None needed |
| Chat system performance | High | Medium | Use Firebase Firestore subcollections | Limit message history (last 50) |
| Solo burnout / scope creep | High | Critical | Strict time-boxing, daily checklist | Cut P1/P2 ruthlessly |

## WEEK-BY-WEEK BREAKDOWN

### WEEK 1: Foundation + Backend Core

Goal: Working API, auth, data model, restaurant listing

### WEEK 2: Mobile Customer App + Ordering

Goal: Customer can browse, add to cart, place order (COD)

### WEEK 3: Driver App + Real-time + Notifications

Goal: Driver receives orders, updates status, customer sees live updates

### WEEK 4: Admin Dashboard + Polish + Store Submission

Goal: Internal admin tools, testing, app store builds submitted

## A) PRODUCT SCOPE & DECISIONS

### MUST DECIDE NOW (Decision Points)

| Decision | Recommendation | Justification |
| --- | --- | --- |
| Restaurant onboarding | Manual (admin adds) | Saves 3-5 days of building restaurant signup |
| Delivery fee | Fixed ₪5,000 IQD (~$3.80 USD) | Simple, iterate post-launch |
| Order radius | 5km from restaurant | Prevents impossible deliveries |
| Driver assignment | Manual (driver accepts from pool) | Auto-assignment = 2-3 extra days |
| Menu variants | Up to 3 variants per item (e.g., size, spice level) | Balances complexity vs flexibility |
| Add-ons | Max 10 per item | Prevents UI chaos |
| Min order value | ₪10,000 IQD (~$7.60) | Reduce unprofitable orders |
| Languages | Arabic (primary) + English | RTL required for Arabic |
| Support hours | 9 AM - 11 PM Iraq time | Chat system works 24/7, admin responds during hours |
| Driver verification | Manual (admin approves after ID check) | No automated KYC in MVP |

### Iraq Compliance Checklist (MUST VERIFY LOCALLY)

- Business registration: Confirm you can operate food delivery legally

- Tax obligations: VAT/sales tax on orders? (Iraq VAT is 15-20% in some sectors)

- Data residency: Any requirement to store user data in Iraq? (Unknown for Iraq)

- Restaurant licensing: Are restaurant partners required to have permits?

- Driver employment status: Independent contractors or employees? (Affects insurance)

- Payment processing: COD is simple, but verify no restrictions

- Consumer protection laws: Refund policy, cancellation policy required?

- Privacy policy: Required? (Assume YES - cover data collection, sharing, retention)

- Terms of service: Required? (Assume YES)

- Age restrictions: Minimum age to order? (Assume 18+)

Action: Consult local lawyer by Day 7. Budget $300-500 for legal review.

## B) DATA MODEL & ENTITIES

### Firestore Collections Structure

users/ (customer, driver, admin)

├─ {userId}/

├─ profile: {name, phone, email, role, addresses[], createdAt}

├─ orders/ (subcollection) → pointer to orders/{orderId}

restaurants/

├─ {restaurantId}/

├─ info: {name, description, image, address, location{lat,lng}, cuisine[], rating, openHours, isActive}

├─ menu_items/ (subcollection)

├─ {itemId}/

├─ {name, description, price, image, category, isAvailable}

├─ variants/ (subcollection)

├─ {variantId}: {name, options[{name, priceModifier}]}

├─ addons/ (subcollection)

├─ {addonId}: {name, price}

orders/

├─ {orderId}/

├─ {customerId, restaurantId, driverId?, items[], subtotal, deliveryFee, total,

status, deliveryAddress, customerPhone, createdAt, timestamps{}, paymentMethod}

├─ tracking/ (subcollection)

├─ {trackId}: {driverLocation{lat,lng}, timestamp, status}

├─ chat/ (subcollection)

├─ {messageId}: {senderId, senderRole, text, timestamp, readBy[]}

drivers/

├─ {driverId}/

├─ {name, phone, vehicle, status: 'available'|'busy'|'offline', currentLocation{lat,lng},

activeOrderId?, rating, completedOrders}

admin_config/

├─ settings: {deliveryFee, minOrderValue, serviceRadius, maintenanceMode}

Why Firestore:

- Real-time listeners for order status, driver location

- Offline support for mobile apps

- Automatic scaling

- No ops overhead

- Free tier: 50K reads/day, 20K writes/day (enough for 100 orders/day)

Alternative: PostgreSQL on Cloud Run for transactional data + Firestore for real-time. Cut decision: Firestore only for MVP (simpler).

## C) BACKEND IMPLEMENTATION (FastAPI)

### Architecture: Modular Monolith

backend/

├─ main.py (entry point)

├─ config.py (env vars, Firebase init)

├─ dependencies.py (auth middleware)

├─ models/ (Pydantic schemas)

│   ├─ user.py

│   ├─ restaurant.py

│   ├─ order.py

│   ├─ driver.py

├─ routers/

│   ├─ auth.py

│   ├─ restaurants.py

│   ├─ orders.py

│   ├─ drivers.py

│   ├─ admin.py

│   ├─ chat.py

├─ services/

│   ├─ firebase_service.py (Firestore CRUD)

│   ├─ notification_service.py (FCM)

│   ├─ mapbox_service.py (geocoding, distance)

│   ├─ order_service.py (business logic)

├─ utils/

│   ├─ validators.py

│   ├─ helpers.py

├─ tests/

└─ requirements.txt

### Tech Stack Justification

- FastAPI: Fast, async, auto docs, type hints, easy to learn

- Firebase Admin SDK (Python): Official, well-maintained, handles auth tokens

- Uvicorn: ASGI server for FastAPI

- Cloud Run: Serverless, auto-scales, free tier (1M requests/month), no Kubernetes overhead

- Firebase Hosting: Static admin dashboard (React/Vue or even plain HTML)

### Hosting Decision: Cloud Run (not App Engine)

Why Cloud Run:

- Containerized (Dockerfile = full control)

- Scales to zero (cost savings)

- Request-based pricing

- WebSocket support (if needed later)

- 5-minute timeout (enough for long-running order processing)

## D) FIREBASE INTEGRATION PLAN

| Service | Purpose | Why This Service | Free Tier Limits | Estimated MVP Cost |
| --- | --- | --- | --- | --- |
| Firebase Auth | User authentication (email/social) | Handles tokens, refresh, social providers | Unlimited free | $0 |
| Firestore | Database (real-time + offline) | Real-time listeners, auto-scaling, no ops | 50K reads/day, 20K writes/day, 1GB storage | $0-10/month |
| Firebase Storage | Restaurant/food images, user avatars | CDN-backed, secure URLs, easy uploads | 5GB storage, 1GB/day download | $0-5/month |
| Cloud Functions | Order triggers, notifications, cleanup | Event-driven, serverless, no server to manage | 2M invocations/month | $0-5/month |
| Firebase Cloud Messaging (FCM) | Push notifications | Free, cross-platform, integrates with Firebase | Unlimited free | $0 |
| Firebase Crashlytics | Crash reporting (Flutter) | Real-time crash alerts, symbolication | Unlimited free | $0 |
| Firebase Analytics | User behavior, funnels | Free, integrated with Firebase | Unlimited free | $0 |
| Firebase Performance | App performance monitoring | Trace network calls, screen loads | Unlimited free | $0 |

Total estimated month 1 cost: $10-20/month (scales with traffic, but 100 orders/day fits free tier mostly)

### Firebase Architecture Decisions

What lives in Firestore:

- User profiles, restaurants, menu items, orders, drivers, chat messages

- Why: Real-time sync, offline support, simple security rules

What lives in Cloud Functions:

- Order placed trigger: Send notifications to restaurant + available drivers

- Order status change trigger: Notify customer, update driver availability

- Nightly cleanup: Archive old chat messages (>30 days)

- Why: Decouple business logic, event-driven, no always-on server cost

What lives in Cloud Run (FastAPI):

- REST APIs for CRUD operations

- Business logic (order validation, delivery fee calculation)

- Admin operations (add restaurant, approve driver)

- Why: Complex business logic, easier to test, Python ecosystem

Data flow:

- Mobile app → FastAPI (Cloud Run) → Firestore (write order)

- Firestore → Cloud Function (trigger) → FCM (send notification)

- Mobile app ← Firestore listener (real-time order status updates)

## E) API SURFACE (HIGH-LEVEL ENDPOINTS)

### Authentication (/auth)

| Endpoint | Method | Auth | Purpose | Request | Response |
| --- | --- | --- | --- | --- | --- |
| /auth/signup | POST | None | Create account | {email, password, name, phone, role} | {userId, token} |
| /auth/login | POST | None | Email login | {email, password} | {userId, token, role} |
| /auth/social | POST | None | Google/Apple login | {provider, idToken} | {userId, token, role} |
| /auth/refresh | POST | Required | Refresh token | {refreshToken} | {token} |

### Restaurants (/restaurants)

| Endpoint | Method | Auth | Purpose | Response |
| --- | --- | --- | --- | --- |
| /restaurants | GET | Customer | List restaurants (with filters) | [{id, name, image, cuisine, rating, eta, isOpen}] |
| /restaurants/{id} | GET | Customer | Restaurant details | {...restaurant, menuItems[]} |
| /restaurants/{id}/menu | GET | Customer | Menu items | [{id, name, price, image, variants[], addons[]}] |

### Orders (/orders)

| Endpoint | Method | Auth | Purpose | Request | Response |
| --- | --- | --- | --- | --- | --- |
| /orders | POST | Customer | Place order | {restaurantId, items[], deliveryAddress, phone} | {orderId, total, eta} |
| /orders/{id} | GET | Customer/Driver/Admin | Get order details | - | {...order, status, driver?, tracking[]} |
| /orders/{id}/status | PATCH | Driver/Admin | Update order status | {status} | {orderId, status, timestamp} |
| /orders/customer/{userId} | GET | Customer | Order history | - | [{orderId, restaurant, total, status, createdAt}] |
| /orders/restaurant/{restaurantId} | GET | Restaurant/Admin | Restaurant orders | - | [{orderId, customer, items, status}] |
| /orders/driver/available | GET | Driver | Available orders (to accept) | - | [{orderId, restaurant, deliveryAddress, fee}] |
| /orders/{id}/accept | POST | Driver | Accept order | - | {orderId, driverId} |

### Drivers (/drivers)

| Endpoint | Method | Auth | Purpose | Request | Response |
| --- | --- | --- | --- | --- | --- |
| /drivers/location | POST | Driver | Update driver location | {lat, lng} | {success} |
| /drivers/status | PATCH | Driver | Update availability | `{status: 'available' | 'busy' |
| /drivers/{id} | GET | Customer/Admin | Get driver details | - | {name, vehicle, rating, phone} |

### Admin (/admin)

| Endpoint | Method | Auth | Purpose | Request | Response |
| --- | --- | --- | --- | --- | --- |
| /admin/restaurants | POST | Admin | Add restaurant | {name, address, location, openHours, ...} | {restaurantId} |
| /admin/restaurants/{id}/menu | POST | Admin | Add menu item | {name, price, category, variants[], addons[]} | {itemId} |
| /admin/drivers | POST | Admin | Approve driver | {driverId} | {success} |
| /admin/orders | GET | Admin | All orders (dashboard) | ?status=&date= | [{orderId, ...}] |

### Chat (/chat)

| Endpoint | Method | Auth | Purpose | Request | Response |
| --- | --- | --- | --- | --- | --- |
| /chat/{orderId}/messages | GET | Customer/Driver | Get chat messages | - | [{messageId, text, senderId, timestamp}] |
| /chat/{orderId}/send | POST | Customer/Driver | Send message | {text} | {messageId, timestamp} |

Note: Most real-time data (order status, driver location, chat) uses Firestore listeners in mobile app, not polling these endpoints.

## F) MOBILE APP IMPLEMENTATION (Flutter)

### Project Structure

lib/

├─ main.dart

├─ config/

│   ├─ theme.dart (Material theme, RTL support)

│   ├─ routes.dart

│   ├─ constants.dart

├─ core/

│   ├─ services/

│   │   ├─ api_service.dart (REST calls to FastAPI)

│   │   ├─ auth_service.dart (Firebase Auth)

│   │   ├─ firestore_service.dart (Firestore listeners)

│   │   ├─ notification_service.dart (FCM)

│   │   ├─ location_service.dart (GPS for driver)

│   ├─ models/ (Order, Restaurant, MenuItem, etc.)

│   ├─ utils/

├─ features/

│   ├─ auth/

│   ├─ customer/

│   │   ├─ home/

│   │   ├─ restaurant_detail/

│   │   ├─ cart/

│   │   ├─ checkout/

│   │   ├─ order_tracking/

│   ├─ driver/

│   │   ├─ available_orders/

│   │   ├─ active_order/

│   │   ├─ order_map/

│   ├─ restaurant/ (if self-service in future)

│   ├─ admin/

│   ├─ chat/

│   ├─ shared/ (widgets, components)

├─ l10n/ (localization files)

│   ├─ app_ar.arb (Arabic)

│   ├─ app_en.arb (English)

### Key Flutter Packages

| Package | Purpose | Why |
| --- | --- | --- |
| firebase_core | Firebase initialization | Required for all Firebase services |
| firebase_auth | Authentication | Official, well-maintained |
| cloud_firestore | Real-time database | Real-time listeners |
| firebase_messaging | Push notifications | FCM integration |
| firebase_crashlytics | Crash reporting | Stability monitoring |
| http or dio | REST API calls | Simple, widely used |
| provider or riverpod | State management | Riverpod recommended (simpler than Bloc for solo dev) |
| flutter_localizations | Localization | Official i18n support |
| intl | Date/number formatting | RTL + locale support |
| mapbox_gl | Maps + driver tracking | Per your requirement |
| geolocator | GPS location | Driver app |
| flutter_local_notifications | Local notifications | Fallback for FCM |
| cached_network_image | Image caching | Performance |
| image_picker | Upload photos (driver/restaurant) | Built-in |

State Management Decision: Use Riverpod (not Bloc) - less boilerplate, easier for solo dev, still scales well.

### RTL Support Checklist

- Set MaterialApp.localizationsDelegates with GlobalMaterialLocalizations.delegate and GlobalWidgetsLocalizations.delegate

- Add supportedLocales: [Locale('ar'), Locale('en')]

- Use Directionality.of(context) to detect RTL

- Test all screens with Arabic text (Day 3)

- Use TextDirection.rtl for Arabic

- Avoid hardcoded Alignment.left - use AlignmentDirectional.start

- Test cart, checkout, order tracking in RTL mode

- Mapbox: Ensure map controls work in RTL

## G) REAL-TIME ARCHITECTURE

### Real-Time Requirements

- Order status updates (Customer sees: pending → preparing → ready → picked up → delivered)

- Driver location tracking (Customer sees driver moving on map)

- Push notifications (Order placed, driver assigned, order delivered)

### Design Decision: Firestore Listeners (Not WebSocket)

Why Firestore:

- Built-in real-time sync

- Offline support (mobile queues writes)

- No custom server infrastructure

- Scales automatically

- Security rules protect data

How it works:

- Order status: Customer app listens to orders/{orderId} document

- Driver location: Customer app listens to orders/{orderId}/tracking subcollection (last 10 locations)

- Driver updates location: Driver app writes to orders/{orderId}/tracking every 10 seconds (only when active)

- Firestore propagates changes: All listeners receive updates in <1 second

Code example (Flutter):

dart

// Customer app - listen to order status

Stream<Order> watchOrder(String orderId) {

return FirebaseFirestore.instance

.collection('orders')

.doc(orderId)

.snapshots()

.map((snap) => Order.fromFirestore(snap));

}

// Customer app - listen to driver location

Stream<List<Location>> watchDriverLocation(String orderId) {

return FirebaseFirestore.instance

.collection('orders')

.doc(orderId)

.collection('tracking')

.orderBy('timestamp', descending: true)

.limit(1)

.snapshots()

.map((snap) => snap.docs.map((d) => Location.fromFirestore(d)).toList());

}

```

### Driver Location Update Strategy

**Battery optimization:**

- Update every 10 seconds when order is active

- Stop updates when idle

- Use `geolocator` package with `desiredAccuracy: LocationAccuracy.medium` (not high - saves battery)

- Background location: Use `flutter_background_geolocation` (requires config, test by Day 10)

**Data volume:**

- 1 order, 30 min delivery = 180 location updates × 50 bytes = ~9KB per order

- 100 orders/day = 900KB/day (negligible)

---

## H) NOTIFICATIONS (FCM/APNs via Firebase)

### Notification Flow

1. **Order placed:**

- Trigger: Firestore `orders/{orderId}` created

- Cloud Function: `onOrderCreated`

- Recipients: Restaurant admin (via FCM token stored in Firestore)

- Message: "New order #1234 from Ahmed - 3 items - IQD 25,000"

2. **Driver assigned:**

- Trigger: Firestore `orders/{orderId}` updated with `driverId`

- Cloud Function: `onDriverAssigned`

- Recipients: Customer

- Message: "Driver Ali is on the way! Track your order."

3. **Order status changes:**

- Trigger: Order status field changes

- Cloud Function: `onOrderStatusChanged`

- Recipients: Customer

- Message: "Your order is ready for pickup!" / "Order delivered!"

### Implementation Checklist

**Backend (Cloud Functions):**

- [ ] Install `firebase-functions` SDK

- [ ] Function: `onOrderCreated` (send to restaurant)

- [ ] Function: `onDriverAssigned` (send to customer)

- [ ] Function: `onOrderStatusChanged` (send to customer)

- [ ] Store FCM tokens in Firestore: `users/{userId}/fcmTokens[]` (array, supports multiple devices)

- [ ] Handle token refresh (Firebase Auth triggers)

**Mobile (Flutter):**

- [ ] Request notification permissions (iOS requires explicit permission)

- [ ] Get FCM token on app start

- [ ] Save token to Firestore: `users/{userId}/fcmTokens`

- [ ] Handle foreground notifications (display in-app alert)

- [ ] Handle background/terminated notifications (navigate to order screen)

- [ ] Handle notification tap (deep link to order)

- [ ] Test on iOS (APNs certificate required - use Firebase console)

**iOS Specific:**

- [ ] Add `GoogleService-Info.plist` to Xcode project

- [ ] Enable Push Notifications capability in Xcode

- [ ] Upload APNs certificate to Firebase Console (or use APNs key - easier)

- [ ] Test on physical device (simulator doesn't support push)

**Android Specific:**

- [ ] Add `google-services.json` to `android/app/`

- [ ] Configure notification icon (white icon on transparent background)

- [ ] Test on physical device or emulator

---

## I) ADMIN DASHBOARD + RESTAURANT ADMIN

### Admin Dashboard

**Purpose:**

- Add/edit restaurants

- Add/edit menu items (with variants/add-ons)

- Approve drivers

- View all orders

- Monitor system health

**Tech Stack:** Simple React SPA or even **HTML + vanilla JS** (for speed)

**Hosting:** Firebase Hosting (free, CDN, SSL, deploy in seconds)

**Authentication:** Firebase Auth (admin role check in Firestore Security Rules)

**Features (MVP):**

- [ ] Restaurant management (CRUD)

- [ ] Menu management (CRUD with variants/add-ons)

- [ ] Driver approval (list pending drivers, approve/reject)

- [ ] Order dashboard (list all orders, filter by status/date)

- [ ] Basic metrics (orders today, total revenue, active drivers)

**Cut decision:** If time is tight, admin can use Firestore Console directly for restaurant/menu management. Focus on driver approval UI (can't do in Firestore Console easily).

### Restaurant Admin (Future - Cut in MVP)

**Recommendation:** Skip restaurant self-service in MVP. Admin adds restaurants + menus manually.

**Why cut:**

- Saves 3-5 days (auth, restaurant signup flow, menu editor UI)

- Manual onboarding builds relationships with restaurants

- Can add post-launch if needed

**If you must include:**

- Restaurant admin logs in, sees orders for their restaurant only

- Can mark items unavailable

- Can update order status (preparing → ready)

- Simple web dashboard (not mobile app)

---

## J) CHAT SYSTEM DESIGN

### Pragmatic Approach: Firestore Subcollections

**Data model:**

```

orders/{orderId}/chat/{messageId}

{

senderId: string,

senderRole: 'customer' | 'driver',

senderName: string,

text: string,

timestamp: Timestamp,

readBy: [userId1, userId2]

}

Why Firestore:

- Real-time listeners (messages appear instantly)

- Simple to implement

- No separate chat server

- Integrated with order lifecycle

Features (MVP):

- Text messages only (no images/voice - cut if time tight)

- Customer ↔ Driver only (not restaurant in MVP)

- Chat thread created automatically when order is placed

- Unread indicator (count messages where readBy doesn't include current user)

- Chat history (last 50 messages)

Limitations (acceptable for MVP):

- No encryption (Firestore data is encrypted at rest, but not end-to-end)

- No typing indicators (add post-launch if needed)

- No message editing/deletion

- No file uploads (can add later if needed)

Performance:

- Limit query to last 50 messages: .limit(50).orderBy('timestamp', descending: true)

- Firestore: 1 read per message (cached after first load)

- 100 orders/day × 5 messages/order = 500 reads/day (well within free tier)

UI:

- Simple chat bubble UI (Flutter package: flutter_chat_ui or build custom)

- Auto-scroll to latest message

- Show sender name + role (customer/driver)

- Timestamp

Cut decision: If you lose time, make chat text-only (no images). If you lose more time, provide phone number on order screen instead of chat (use phone's native SMS/call).

## K) SECURITY & PRIVACY BASELINE

### Firestore Security Rules (Critical - Define by Day 7)

javascript

rules_version = '2';

service cloud.firestore {

match /databases/{database}/documents {

// Helper functions

function isAuthenticated() {

return request.auth != null;

}

function isOwner(userId) {

return request.auth.uid == userId;

}

function isAdmin() {

return isAuthenticated() &&

get(/databases/$(database)/documents/users/$(request.auth.uid)).data.role == 'admin';

}

function isDriver() {

return isAuthenticated() &&

get(/databases/$(database)/documents/users/$(request.auth.uid)).data.role == 'driver';

}

// Users

match /users/{userId} {

allow read: if isOwner(userId) || isAdmin();

allow create: if isAuthenticated();

allow update: if isOwner(userId) || isAdmin();

}

// Restaurants (public read)

match /restaurants/{restaurantId} {

allow read: if true;

allow write: if isAdmin();

match /menu_items/{itemId} {

allow read: if true;

allow write: if isAdmin();

}

}

// Orders

match /orders/{orderId} {

allow read: if isOwner(resource.data.customerId) ||

isOwner(resource.data.driverId) ||

isAdmin();

allow create: if isAuthenticated();

allow update: if isOwner(resource.data.driverId) || isAdmin();

match /tracking/{trackId} {

allow read: if isOwner(get(/databases/$(database)/documents/orders/$(orderId)).data.customerId) ||

isOwner(get(/databases/$(database)/documents/orders/$(orderId)).data.driverId);

allow write: if isDriver();

}

match /chat/{messageId} {

allow read: if isOwner(get(/databases/$(database)/documents/orders/$(orderId)).data.customerId) ||

isOwner(get(/databases/$(database)/documents/orders/$(orderId)).data.driverId);

allow create: if isAuthenticated();

}

}

// Drivers

match /drivers/{driverId} {

allow read: if isAuthenticated();

allow write: if isAdmin();

}

}

}

Test security rules: Use Firebase Console > Firestore > Rules Playground (Day 8)

### Privacy Policy & Terms of Service

Required: Yes (App Store requires privacy policy link)

Content (minimum):

- What data you collect (name, email, phone, location, orders)

- Why you collect it (to provide delivery service)

- Who you share it with (restaurants, drivers - only for order fulfillment)

- How long you keep it (until user deletes account)

- User rights (access, delete account)

- Contact info

Action: Use a privacy policy generator (e.g., https://www.freeprivacypolicy.com/) - 1 hour

Hosting: Firebase Hosting (yourapp.com/privacy, yourapp.com/terms)

### PII Protection Checklist

- Never log passwords, tokens, or full credit card numbers (COD only, so N/A)

- Never expose user phone/email in public API responses (only to authorized roles)

- Hash driver/restaurant IDs in public URLs (prevents enumeration)

- Rate limit login attempts (Firebase Auth handles this)

- Validate all inputs (Pydantic models in FastAPI)

- Sanitize chat messages (prevent XSS if displaying in web dashboard)

### Abuse Prevention (Basic)

- Rate limiting on order creation: Max 5 orders/hour per user (Firestore Security Rules or Cloud Function)

- Require phone verification (Firebase Auth SMS - costs $0.01/SMS after free tier)

Blockusers with >3 cancelled orders in 24h (manual review by admin)

- Driver approval: Manual review of ID documents before activation

## L) OBSERVABILITY & OPERATIONS

### Logging

Backend (FastAPI on Cloud Run):

- Use logging module (Python standard library)

- Log to stdout (Cloud Run auto-captures to Cloud Logging)

- Log levels: INFO (requests), WARNING (validation errors), ERROR (exceptions)

- Structured logging: JSON format (easier to query)

- Include request ID, user ID in logs

Example:

python

import logging

logger = logging.getLogger(__name__)

@app.post("/orders")

async def create_order(order: OrderCreate, user_id: str = Depends(get_current_user)):

logger.info(f"Creating order for user {user_id}", extra={"user_id": user_id, "restaurant_id": order.restaurant_id})

Cloud Functions:

- Use console.log() (auto-captured by Cloud Logging)

- Include context: order ID, user ID

Mobile (Flutter):

- Use Firebase Crashlytics (automatic crash reporting)

- Use Firebase Performance Monitoring (network requests, screen load times)

- Custom logs: FirebaseCrashlytics.instance.log("Order placed: $orderId")

### Crash Reporting

- Firebase Crashlytics: Automatic crash reports with stack traces

- Set user ID: FirebaseCrashlytics.instance.setUserIdentifier(userId)

- Test crash: Add a button in debug mode to throw exception

### Metrics & Alerts

Key Metrics (Day 1):

| Metric | Tool | Alert Threshold |
| --- | --- | --- |
| API error rate | Cloud Monitoring | >5% |
| Order creation failures | Custom counter in Cloud Function | >10/hour |
| Firestore read/write quota | Firebase Console | >80% of quota |
| App crash rate | Firebase Crashlytics | >1% |
| FCM delivery failure rate | FCM Console | >10% |

Set up alerts:

- Cloud Monitoring: Alert if API error rate >5% for 5 minutes

- Firebase: Budget alert at $20/month (email notification)

### Monitoring Dashboard (Simple)

Use: Firebase Console + Cloud Monitoring (free)

Key charts (check daily):

- Orders created today

- Active users

- API request count

- Firestore reads/writes

- Cloud Run CPU/memory usage

- App crash-free rate

## M) QA/TESTING PLAN

### Unit Tests (Backend)

Target: 70% coverage on business logic (order service, validation)

Framework: pytest

Example tests:

- Order total calculation (items + delivery fee)

- Delivery fee logic (fixed for MVP)

- Variant/addon price calculation

- Address validation

- Phone number format validation

Time budget: 2 days (integrate into Week 2)

### Integration Tests (Backend)

Target: API endpoints with Firestore

Approach: Use Firebase Emulator Suite (local Firestore)

Example tests:

- POST /orders creates order in Firestore

- GET /orders/{id} returns correct order

- PATCH /orders/{id}/status updates status and triggers Cloud Function

Time budget: 1 day (Week 3)

### E2E Tests (Mobile)

Framework: integration_test (Flutter built-in)

Critical flows:

- Sign up → Browse restaurants → Add to cart → Checkout → Place order

- Driver: Login → See available orders → Accept order → Update status

- Customer: Track order → Receive notifications → Chat with driver

Time budget: 2 days (Week 4) - Can cut if time tight

Alternative: Manual testing with test script

### Manual Test Script (Critical Flows)

Customer flow:

- Sign up with email/password

- Browse restaurants (Arabic + English)

- Search for specific cuisine

- View restaurant details + menu

- Add item to cart with variants/add-ons

- View cart (correct total)

- Checkout with delivery address

- Place order (COD)

- Receive "order placed" notification

- View order status (real-time updates)

- Track driver on map (when assigned)

- Chat with driver

- View order history

Driver flow:

- Login

- See available orders

- Accept order

- View customer address on map

- Start navigation (Mapbox)

- Update order status (picked up → delivered)

- Chat with customer

- View earnings (simple list)

Restaurant admin flow (if built):

- Login

- See new orders

- Mark order as preparing/ready

Admin flow:

- Login to dashboard

- Add new restaurant

- Add menu items with variants

- Approve driver

- View all orders

Time budget: 3 days (Week 4)

### Device Testing

iOS:

- iPhone (physical device - borrow or rent)

- Test on iOS 15+ (minimum supported version)

- Test RTL (Arabic) layout

- Test notifications (APNs)

Android:

- Android 9+ (minimum supported version)

- Test on emulator + physical device

- Test RTL layout

- Test notifications (FCM)

Time budget: 2 days (Week 4)

### Performance Testing

Target: App loads in <3 seconds on 3G

Tools:

- Firebase Performance Monitoring (automatic)

- Lighthouse (for web dashboard)

Checklist:

- Optimize images (use WEBP, compress, lazy load)

- Cache restaurant/menu data (Firestore offline persistence)

- Minimize API calls (batch requests where possible)

- Test on slow network (Chrome DevTools throttling)

Time budget: 1 day (Week 4) - Can cut if time tight

## N) RELEASE & STORE SUBMISSION

### Pre-Submission Checklist

iOS (TestFlight → App Store):

- App Store Connect: Create app listing

- App metadata: Name, description (Arabic + English), keywords, category (Food & Drink)

- Screenshots: 6.5" (iPhone 14 Pro Max), 5.5" (iPhone 8 Plus) - Arabic + English

- Privacy policy: Upload to yourapp.com/privacy, add link in App Store Connect

- App icon: 1024×1024 (no transparency, no alpha channel)

- Build: Archive in Xcode, upload to App Store Connect

- TestFlight: Invite 5-10 beta testers, collect feedback (3 days)

- App Review Information: Demo account credentials (customer, driver), test phone number

- Export Compliance: Select "No" if no encryption (or "Yes" for HTTPS - usually exempt)

- Content Rights: Confirm you have rights to all images/content

- Age Rating: 4+ (no objectionable content)

Android (Internal Test → Production):

- Google Play Console: Create app

- App metadata: Title, short description, full description (Arabic + English), category (Food & Drink)

- Screenshots: Phone (1080×1920), tablet (1200×1920) - Arabic + English

- Privacy policy: URL

- App icon: 512×512 (PNG)

- Content rating: Complete questionnaire (usually PEGI 3, ESRB Everyone)

- Build: Generate signed APK/AAB, upload to Internal Test track

- Internal testing: Invite 5-10 testers, collect feedback (3 days)

- Data safety form: Declare data collection (location, contact info, etc.)

- Target audience: All ages (or 18+ if required)

- Roll out: Internal → Closed Beta → Open Beta → Production (can skip beta for MVP)

### App Store Review Tips (iOS)

Common rejections:

- Crashes on launch (test thoroughly)

- Missing privacy policy

- Incomplete app (obvious placeholder content)

- Violates guidelines (e.g., inappropriate content)

- Requires login but no demo account provided

Mitigation:

- Provide demo accounts (customer, driver, restaurant) with test data

- Add "Demo Mode" toggle in settings (if helpful)

- Test on physical device before submission

- Respond to reviewer feedback quickly (24-48 hours)

Typical review time: 1-3 days (can be 24 hours if lucky)

### Launch Day Checklist

- Soft launch: Release to Iraq only (geofence in App Store/Play Store)

- Monitor: Check Crashlytics, Cloud Monitoring, Firestore usage

- Support: Have customer support channel ready (in-app chat + phone/email)

- Marketing: Announce on social media, local groups

- Feedback: Collect user feedback (in-app prompt after 3 orders)

- Rollout: Start with 10% of users (Play Store staged rollout), monitor for 24 hours, increase to 50%, then 100%

## DAY-BY-DAY BREAKDOWN (30 DAYS)

### WEEK 1: BACKEND FOUNDATION (Days 1-7)

#### Day 1: Project Setup + Decisions

- What: Create Firebase project, enable services (Auth, Firestore, Storage, Cloud Functions, FCM)

  - Why: Foundation for entire stack

  - DoD: Firebase Console shows active project, billing enabled (free tier), services enabled

- What: Create GitHub repo, set up FastAPI project structure

  - Why: Version control, code organization

  - DoD: git push works, main.py runs locally with "Hello World"

- What: Finalize scope decisions (use table above)

  - Why: No scope creep

  - DoD: Decision log documented (can be in README)

- What: Start legal compliance checklist (consult lawyer if possible)

  - Why: Avoid legal issues post-launch

  - DoD: Email sent to lawyer, or research started

#### Day 2: Data Model + Auth

- What: Design Firestore collections (users, restaurants, menu_items, orders, drivers)

  - Why: Database schema drives everything

  - DoD: Firestore structure documented, sample data added manually

- What: Implement Firebase Auth in FastAPI (verify ID tokens)

  - Why: Secure API endpoints

  - Dependencies: Firebase project created

  - DoD: /auth/signup and /auth/login work, return JWT token

- What: Create Pydantic models (User, Restaurant, Order, etc.)

  - Why: Type safety, validation

  - DoD: Models defined in models/ folder

#### Day 3: Core API Endpoints (Restaurants)

- What: Implement /restaurants (list) and /restaurants/{id} (detail)

  - Why: Customer needs to browse restaurants

  - Dependencies: Firestore schema, Auth

  - DoD: API returns restaurant list, detail page with menu items

- What: Implement /restaurants/{id}/menu (menu items with variants/add-ons)

  - Why: Customer needs to see menu

  - DoD: API returns menu items with nested variants/add-ons

- What: Add sample restaurants + menus to Firestore

  - Why: Test data for mobile app

  - DoD: 3 restaurants with 5-10 menu items each

#### Day 4: Order API

- What: Implement POST /orders (create order)

  - Why: Core business logic

  - Dependencies: Menu API, Auth

  - DoD: Order created in Firestore, total calculated correctly, returns order ID

- What: Implement GET /orders/{id} (order details)

  - Why: Customer/driver need to see order

  - DoD: API returns order with items, status, customer/driver info

- What: Implement PATCH /orders/{id}/status (update order status)

  - Why: Driver updates status

  - DoD: Status updates in Firestore, returns success

#### Day 5: Driver API + Mapbox

- What: Implement /drivers/location (update driver GPS)

  - Why: Real-time tracking

  - Dependencies: Firestore schema

  - DoD: Driver location saved to orders/{orderId}/tracking subcollection

- What: Implement GET /orders/driver/available (available orders)

  - Why: Driver needs to see orders to accept

  - DoD: API returns orders with status "pending"

- What: Integrate Mapbox (geocoding API for address → lat/lng)

  - Why: Validate delivery addresses

  - DoD: POST /orders converts address string to lat/lng via Mapbox

#### Day 6: Cloud Functions (Notifications)

- What: Create Cloud Function: onOrderCreated (notify restaurant)

  - Why: Restaurant needs to know about new orders

  - Dependencies: Firestore, FCM tokens in user profile

  - DoD: Function triggers when order created, sends FCM notification to restaurant

- What: Create Cloud Function: onDriverAssigned (notify customer)

  - Why: Customer needs to know driver assigned

  - DoD: Function triggers when order.driverId updated, sends FCM to customer

- What: Deploy Cloud Functions to Firebase

  - Why: Test end-to-end notification flow

  - DoD: firebase deploy --only functions succeeds, functions visible in Firebase Console

#### Day 7: Admin API + Firestore Security Rules

- What: Implement POST /admin/restaurants (add restaurant)

  - Why: Admin needs to onboard restaurants

  - Dependencies: Auth (admin role check)

  - DoD: Restaurant created in Firestore, returns restaurant ID

- What: Implement POST /admin/restaurants/{id}/menu (add menu item)

  - Why: Admin manages menus

  - DoD: Menu item created with variants/add-ons

- What: Define Firestore Security Rules (see section K)

  - Why: Prevent unauthorized access

  - DoD: Rules deployed, tested in Rules Playground

- What: Deploy FastAPI to Cloud Run

  - Why: Mobile app needs live API

  - DoD: API accessible at https://yourapp-xyz.run.app, health check returns 200

End of Week 1 Goal: Backend API live, sample data in Firestore, notifications working

### WEEK 2: MOBILE CUSTOMER APP (Days 8-14)

#### Day 8: Flutter Project Setup + Auth

- What: Create Flutter project, add Firebase SDKs

  - Why: Foundation for mobile app

  - DoD: flutter run works on emulator, Firebase initialized

- What: Set up localization (Arabic + English)

  - Why: RTL support required

  - DoD: MaterialApp shows Arabic text correctly, RTL layout works

- What: Implement login/signup screens (email/password)

  - Why: User authentication

  - Dependencies: Backend auth API

  - DoD: User can sign up, login, token saved locally (secure storage)

#### Day 9: Home Screen + Restaurant List

- What: Build home screen (restaurant list with filters)

  - Why: Customer browses restaurants

  - Dependencies: /restaurants API

  - DoD: Grid/list view of restaurants, search by cuisine, sort by rating

- What: Add pull-to-refresh

  - Why: User can refresh restaurant list

  - DoD: Pull down gesture refreshes data

- What: Add loading states, error handling

  - Why: Better UX

  - DoD: Shimmer loading, error message if API fails

#### Day 10: Restaurant Detail + Menu

- What: Build restaurant detail screen (menu items, categories)

  - Why: Customer sees menu

  - Dependencies: /restaurants/{id}/menu API

  - DoD: Menu items grouped by category, images load, prices display

- What: Build menu item detail (variants, add-ons)

  - Why: Customer customizes order

  - DoD: Modal shows item, variants (radio buttons), add-ons (checkboxes), price updates

- What: Implement "Add to Cart"

  - Why: Customer builds order

  - DoD: Item added to cart (in-memory state), cart badge shows count

#### Day 11: Cart + Checkout

- What: Build cart screen (list items, edit quantities, remove)

  - Why: Customer reviews order

  - Dependencies: Cart state management (Riverpod)

  - DoD: Cart shows items with variants/add-ons, subtotal + delivery fee, total

- What: Build checkout screen (delivery address, phone, COD)

  - Why: Customer confirms order

  - DoD: Address input (autocomplete with Mapbox?), phone validation, payment method (COD only)

- What: Implement "Place Order" (POST /orders)

  - Why: Core transaction

  - DoD: Order created, navigates to order tracking screen

#### Day 12: Order Tracking + Real-Time

- What: Build order tracking screen (status, driver info, map)

  - Why: Customer sees order progress

  - Dependencies: Firestore listener on orders/{orderId}

  - DoD: Status updates in real-time (pending → preparing → ready → picked up → delivered)

- What: Implement driver location tracking (map with marker)

  - Why: Customer sees driver moving

  - Dependencies: Firestore listener on orders/{orderId}/tracking

  - DoD: Driver marker moves on map as location updates

- What: Add Mapbox integration (show map, route)

  - Why: Visual tracking

  - DoD: Map shows restaurant, delivery address, driver location (if available)

#### Day 13: Notifications + Order History

- What: Implement FCM setup (get token, save to Firestore)

  - Why: Receive notifications

  - DoD: FCM token saved on app start, visible in Firestore

- What: Handle foreground/background notifications

  - Why: User sees order updates

  - DoD: Notification banner shows when order status changes, tapping navigates to order

- What: Build order history screen (past orders)

  - Why: Customer can reorder

  - Dependencies: GET /orders/customer/{userId} API

  - DoD: List of past orders with status, date, total

#### Day 14: Polish + Testing (Customer App)

- What: Test RTL layout (Arabic)

  - Why: Must work correctly

  - DoD: All screens render correctly in Arabic, no text overflow

- What: Add empty states (no restaurants, no orders)

  - Why: Better UX

  - DoD: Friendly message + illustration when empty

- What: Test end-to-end flow (signup → browse → order → track)

  - Why: Catch bugs

  - DoD: Manual test script completed, bugs logged

- What: Fix critical bugs from testing

  - Why: Stability

  - DoD: App doesn't crash, core flow works

End of Week 2 Goal: Customer can browse, order, track in real-time

### WEEK 3: DRIVER APP + CHAT (Days 15-21)

#### Day 15: Driver App Setup + Available Orders

- What: Create driver-specific screens (or role-based routing in same app)

  - Why: Driver has different workflow

  - DoD: Driver role redirects to driver home screen

- What: Build available orders screen (list pending orders)

  - Why: Driver picks orders

  - Dependencies: GET /orders/driver/available API

  - DoD: List shows order ID, restaurant, delivery address, fee

- What: Implement "Accept Order" (POST /orders/{id}/accept)

  - Why: Driver claims order

  - DoD: Order assigned to driver, status changes to "accepted"

#### Day 16: Active Order + Navigation

- What: Build active order screen (customer info, items, address)

  - Why: Driver sees order details

  - Dependencies: Firestore listener on orders/{orderId}

  - DoD: Screen shows customer name, phone, items, delivery address

- What: Add "Start Navigation" (open Mapbox/Google Maps app)

  - Why: Driver navigates to customer

  - DoD: Tap button opens navigation app with customer address

- What: Implement location tracking (background GPS)

  - Why: Customer sees driver location

  - Dependencies: geolocator package, background location permission

  - DoD: Driver location updates to Firestore every 10 seconds when order active

#### Day 17: Order Status Updates + Notifications

- What: Add status buttons (Picked Up, Delivered)

  - Why: Driver updates order progress

  - Dependencies: PATCH /orders/{id}/status API

  - DoD: Status updates in Firestore, customer receives notification

- What: Test driver notifications (order assigned)

  - Why: Driver knows when new order comes

  - DoD: Driver receives FCM notification when assigned to order

- What: Build driver profile screen (earnings, stats)

  - Why: Driver sees performance

  - DoD: Shows completed orders count, total earnings (simple calculation)

#### Day 18: Chat System (Backend + Mobile)

- What: Implement chat API (GET /chat/{orderId}/messages, POST /chat/{orderId}/send)

  - Why: Customer ↔ Driver communication

  - Dependencies: Firestore subcollection

  - DoD: API returns messages, creates new messages

- What: Build chat screen (Flutter)

  - Why: In-app messaging

  - Dependencies: Firestore listener on orders/{orderId}/chat

  - DoD: Messages display in real-time, user can send text

- What: Add unread badge (count unread messages)

  - Why: User knows new message arrived

  - DoD: Badge shows count of messages where readBy doesn't include user ID

#### Day 19: Chat Polish + Testing

- What: Add sender name/role to messages

  - Why: Distinguish customer vs driver

  - DoD: Message bubbles show "You" vs "Customer" or "Driver"

- What: Test chat (customer ↔ driver, real-time)

  - Why: Catch bugs

  - DoD: Messages appear instantly, no race conditions

- What: Add "Mark as Read" (update readBy array)

  - Why: Unread badge clears

  - DoD: Opening chat marks messages as read

#### Day 20: Driver App Testing

- What: Test driver flow end-to-end (login → see orders → accept → navigate → deliver)

  - Why: Ensure driver app works

  - DoD: Manual test script completed, bugs logged

- What: Fix critical driver app bugs

  - Why: Stability

  - DoD: App doesn't crash, core flow works

- What: Test background location tracking (battery impact)

  - Why: Ensure acceptable battery drain

  - DoD: Location updates work, battery drain <10%/hour

#### Day 21: Buffer Day (Catch Up)

- What: Finish incomplete tasks from Week 3

  - Why: Stay on schedule

  - DoD: All Week 3 tasks marked done

- What: Code review + refactoring

  - Why: Code quality

  - DoD: No obvious bugs, code is readable

- What: Update documentation (API docs, README)

  - Why: Maintainability

  - DoD: README has setup instructions, API docs updated

End of Week 3 Goal: Driver can accept orders, navigate, update status, chat works

### WEEK 4: ADMIN DASHBOARD + QA + RELEASE (Days 22-30)

#### Day 22: Admin Dashboard Setup

- What: Create simple React app (or HTML + vanilla JS)

  - Why: Admin needs UI to manage app

  - DoD: Basic React app with routing (restaurants, menu, drivers, orders)

- What: Implement Firebase Auth login (admin role check)

  - Why: Secure admin dashboard

  - DoD: Admin can log in, non-admins redirected

- What: Deploy to Firebase Hosting

  - Why: Live dashboard

  - DoD: Dashboard accessible at yourapp.web.app

#### Day 23: Restaurant + Menu Management

- What: Build restaurant CRUD (list, add, edit)

  - Why: Admin onboards restaurants

  - Dependencies: POST /admin/restaurants API

  - DoD: Admin can add/edit restaurants with name, address, image, hours

- What: Build menu item CRUD (add item with variants/add-ons)

  - Why: Admin manages menus

  - DoD: Admin can add menu item, specify variants (size, spice), add-ons (extra cheese)

- What: Add image upload (Firebase Storage)

  - Why: Restaurant/item images

  - DoD: Admin can upload images, URLs saved to Firestore

#### Day 24: Driver Approval + Order Dashboard

- What: Build driver approval screen (list pending drivers, approve/reject)

  - Why: Admin verifies drivers

  - DoD: Admin sees driver applications, can approve (sets status to "active")

- What: Build order dashboard (list all orders, filter by status/date)

  - Why: Monitor operations

  - DoD: Table shows order ID, customer, restaurant, driver, status, date, total

- What: Add basic metrics (orders today, revenue)

  - Why: Business insights

  - DoD: Dashboard shows count of orders today, total revenue

#### Day 25: Testing + Bug Fixes

- What: Run manual test scripts (customer, driver, admin flows)

  - Why: Final QA

  - DoD: All critical flows tested, bugs logged

- What: Fix P0 bugs (blockers)

  - Why: Must ship

  - DoD: No crashes, core flows work

- What: Test on physical devices (iOS + Android)

  - Why: Catch device-specific issues

  - DoD: App runs on iPhone, Android phone, no major issues

#### Day 26: Store Preparation (iOS)

- What: Create App Store Connect listing

  - Why: Required for submission

  - DoD: App created, metadata filled (name, description, keywords)

- What: Take screenshots (Arabic + English, all required sizes)

  - Why: App Store requirement

  - DoD: Screenshots uploaded to App Store Connect

- What: Write privacy policy, upload to Firebase Hosting

  - Why: App Store requirement

  - DoD: Privacy policy at yourapp.com/privacy, URL added to App Store Connect

- What: Create Xcode archive, upload to App Store Connect

  - Why: TestFlight + review

  - DoD: Build uploaded, appears in TestFlight

#### Day 27: Store Preparation (Android)

- What: Create Google Play Console listing

  - Why: Required for submission

  - DoD: App created, metadata filled

- What: Take screenshots (Arabic + English)

  - Why: Play Store requirement

  - DoD: Screenshots uploaded

- What: Complete content rating questionnaire

  - Why: Play Store requirement

  - DoD: Rating received (likely PEGI 3 or Everyone)

- What: Generate signed AAB, upload to Internal Test track

  - Why: Internal testing + production

  - DoD: AAB uploaded, internal test track active

#### Day 28: Beta Testing

- What: Invite 5-10 beta testers (TestFlight + Play Store Internal)

  - Why: Real-world testing

  - DoD: Testers invited, install app

- What: Collect feedback, fix critical bugs

  - Why: Polish before launch

  - DoD: Feedback reviewed, P0 bugs fixed

- What: Deploy bug fixes, re-upload builds if needed

  - Why: Stable release

  - DoD: Builds updated in stores

#### Day 29: Final Submission

- What: Submit iOS app for review

  - Why: App Store approval needed

  - DoD: App submitted, status "Waiting for Review"

- What: Promote Android app from Internal to Production

  - Why: Launch

  - DoD: App submitted for review (or published if auto-approved)

- What: Set up monitoring alerts (Crashlytics, Cloud Monitoring)

  - Why: Catch issues post-launch

  - DoD: Alerts configured, email notifications set

- What: Prepare launch announcement (social media, website)

  - Why: Marketing

  - DoD: Posts drafted, ready to publish

#### Day 30: Launch Day + Monitoring

- What: Monitor app store reviews, approve if needed

  - Why: Go live

  - DoD: iOS app approved (or in review), Android app live

- What: Monitor Crashlytics, Firebase Console, Cloud Monitoring

  - Why: Catch launch issues

  - DoD: No critical crashes, error rate <1%

- What: Announce launch on social media

  - Why: Drive installs

  - DoD: Posts published

- What: Provide customer support (monitor chat, respond to issues)

  - Why: User satisfaction

  - DoD: Active monitoring for first 24 hours

- What: Celebrate! 🎉

  - Why: You shipped!

  - DoD: App is live, first order placed

End of Week 4 Goal: App live on App Store + Play Store, users can order

## COMPLIANCE & LEGAL (IRAQ-SPECIFIC)

### MUST VERIFY BEFORE LAUNCH

| Item | Question | Where to Check | Action if Blocked |
| --- | --- | --- | --- |
| Business license | Can I operate food delivery in Iraq? | Ministry of Trade, local chamber of commerce | Halt launch, get license |
| Tax registration | Do I need VAT registration? | General Commission for Taxes | Register if required |
| Food safety | Are restaurants required to have permits? | Ministry of Health | Require restaurant licenses |
| Data privacy | Any data residency laws? | Local tech lawyer | Store data in Iraq region (Firebase Middle East) |
| Payment regulations | Any restrictions on COD? | Central Bank of Iraq | None expected for COD |
| Employment law | Are drivers employees or contractors? | Ministry of Labor | Clarify in driver agreement |
| Consumer protection | Refund/cancellation policy required? | Consumer protection agency | Add policy to app |
| App store compliance | Any Iraq-specific app rules? | Apple/Google policies | Follow policies |

CRITICAL: Consult a local lawyer in Iraq (budget $300-500) by Day 7. Do not launch without basic legal review.

Recommended lawyer search:

- Iraq Bar Association

- Online platforms: Upwork, Fiverr (search "Iraq business lawyer")

- Local tech communities (Facebook groups, LinkedIn)

## FINAL CHECKLIST (PRE-LAUNCH)

### Technical Readiness

- Backend API deployed to Cloud Run, health check returns 200

- Firestore Security Rules deployed, tested

- Cloud Functions deployed, notifications working

- Mobile app builds on iOS + Android

- FCM notifications working (iOS + Android)

- Real-time order tracking working

- Chat system working

- Admin dashboard accessible, auth working

- Privacy policy + Terms of Service live

### Data & Content

- 10+ restaurants with menus in Firestore (real or realistic test data)

- Sample orders created for testing

- 3-5 approved drivers in system

### Testing

- Manual test scripts completed (customer, driver, admin)

- Tested on physical iOS device

- Tested on physical Android device

- Tested with Arabic (RTL) layout

- No crashes in critical flows

- Error rate <1% (monitored via Crashlytics)

### Store Submission

- iOS: App submitted, TestFlight tested

Android: App uploaded to Internal Track, tested [ ] Screenshots (Arabic + English) uploaded

- Privacy policy URL added

- Demo accounts created for reviewers

### Legal & Compliance

- Lawyer consulted (or legal research completed)

- Business license obtained (if required)

- Privacy policy covers data collection, sharing, retention

- Terms of Service cover refunds, cancellations, liability

### Operations

- Monitoring alerts configured (Crashlytics, Cloud Monitoring)

- Customer support channel ready (in-app chat + phone/email)

- Launch announcement prepared

## ESTIMATED COSTS (MONTH 1)

| Item | Cost |
| --- | --- |
| Firebase (free tier likely sufficient) | $0-20 |
| Cloud Run (free tier likely sufficient) | $0-10 |
| Mapbox (free tier: 50K requests/month) | $0 |
| Domain name (optional) | $10-15 |
| Legal consultation | $300-500 |
| Apple Developer Account (annual) | $99 |
| Google Play Developer Account (one-time) | $25 |
| TOTAL | $434-669 |

After launch (monthly):

- Firebase: $10-50 (scales with usage)

- Cloud Run: $5-30

- Mapbox: $0-10 (if under 50K requests)

- Total: $15-90/month (for 100-500 orders/day)

## WHAT TO CUT IF YOU LOSE TIME

### If you lose 3 days:

- Cut social login (email/password only)

- Cut order history (customer can only see active order)

- Cut driver earnings screen (admin tracks manually)

### If you lose 1 week:

- Cut chat system (provide phone number on order screen)

- Cut restaurant self-service (admin adds menus manually)

- Simplify driver tracking (update every 30 seconds instead of 10)

- Cut add-ons (keep variants only)

### If you lose 2 weeks:

- Cut driver app real-time tracking (driver calls customer)

- Cut admin dashboard (use Firestore Console)

- Launch with 5 restaurants only (manual onboarding post-launch)

- Cut ratings & reviews

- Cut advanced search/filters

### Absolute Minimum Shippable (if disaster):

- Customer can browse restaurants, add to cart, place order (COD)

- Restaurant receives order (via notification or SMS)

- Driver receives order (via notification or SMS), updates status manually (via admin or simple UI)

- No real-time tracking (customer calls driver for status)

- No chat (customer calls driver)

- Admin uses Firestore Console to manage data

This is your nuclear option. It's ugly, but it works end-to-end.

## SUCCESS CRITERIA (WEEK 4)

### Definition of "Production-Ready MVP"

- ✅ Functional: Customer can browse, order, track, receive food

- ✅ Stable: <1% crash rate, no data loss

- ✅ Secure: Auth works, Firestore rules prevent unauthorized access

- ✅ Compliant: Privacy policy, terms of service, legal basics covered

- ✅ Live: Published on App Store + Play Store (or in review)

- ✅ Monitored: Crashlytics, Cloud Monitoring, alerts configured

- ✅ Supported: Customer support channel ready

### Post-Launch (Week 5+)

- Monitor first 100 orders

- Collect user feedback

- Fix bugs, optimize performance

- Add P1/P2 features (ratings, promo codes, etc.)

- Scale marketing, onboard more restaurants

## YOU CAN DO THIS

30 days is tight, but doable for a solo developer with:

- Clear scope (use cut-lines ruthlessly)

- Managed services (Firebase does the heavy lifting)

- Focus on core flows (browse → order → deliver)

- Pragmatic architecture (monolith, not microservices)

Your advantages:

- Flutter = one codebase for iOS + Android

- Firebase = no ops, auto-scaling, generous free tier

- FastAPI = fast to build, type-safe, good docs

- Cloud Run = serverless, scales to zero, cheap

Keys to success:

- Time-box everything (if a task takes >1 day, cut scope)

- Test early (don't wait until Week 4 to test RTL)

- Cut ruthlessly (use priority matrix above)

- Ask for help (local lawyer, beta testers, online communities)

- Don't perfectionism (ship MVP, iterate post-launch)

Good luck! 🚀